## Sheet1
|  | BUGS |  | 2023-11-07 | 2023-11-08
DATE: 07-11-2023
S.NO | FORM | DESCRIPTION | Assign To
1 | KRA & KPI | User Screen name itself wrong | Mythili | completed
2 | KRA & KPI | For the user - need to allow only for viewing the document | Mythili | completed
3 | KRA & KPI | Prevent the DELETE, EDIT and ADD new Form for the User | Mythili | completed
4 | KRA & KPI | Need to Change the BreadCrumbs to KRA & KPI | Mythili | completed
5 | KRA & KPI | Excel should not to be redirect to the blank page | Mythili |  | completed
6 | KRA & KPI | Pagination just shows Zero entries | Mythili |  | completed
7 | Let's Talk | While updating - description is not fetching | Mythili | completed
8 | Let's Talk | In description box textarea - by default it gives more white spaces | Mythili | completed
9 | Let's Talk | Implement description - in the list | Mythili | completed
10 | KRA & KPI | Need to change the design for the Save button | Mythili | completed
11 | Festival Creation | In description box textarea - by default it gives more white spaces | Mythili | completed
12 | Staff Creation | Account Details - If the account details is added, Salary type is not listed in the sublist | Mythili | completed
13 | Staff Creation | Account Details - while updating the account details, Bank Status is not fetching | Mythili |  | pending
14 | Staff Creation | Account Details - If we try to add another account details it shows already exist. But the form value is still exist, need clear the value in the field. | Mythili |  | pending
15 | Staff Creation | Experience Details - delete action is not working in the sublist | Mythili |  | completed
16 | Staff Creation | Experience Details - Company name column in the list shows "Undefined" | Mythili |  | completed
17 | Staff Creation | Asset/Vehicle Details - While updating the existing record, status is not fetching | Mythili |  | pending
18 | KRA & KPI | Give uppercase to the every word starting letter in UserScreen Name | Mythili | completed