## Sheet1
DATE : 30-10-2023
S.NO | PROJECT | MODULE | TASK DESCRIPTION | Est.Time | Wrk.Time | Status
1 | xeon | dashboard | lets talk table data get count click window popup delete button list wise data | 6 | 6 | completed
DATE : 31-10-2023
S.NO | PROJECT | MODULE | TASK DESCRIPTION | Est.Time | Wrk.Time | Status
1 | xeon | dashboard | lets talk table data get count click window popup filter with list show and date format change | 6 | 6 | completed
DATE : 01-11-2023
S.NO | PROJECT | MODULE | TASK DESCRIPTION | Est.Time | Wrk.Time | Status
1 | xeon | dashboard | correction lets talk window popup filter with list and festival creation description show | 1.00` | 1 | completed
2 | xeon | Human Resource | The KRA & KPA forms implementation - includes a master form with multiple document upload fields, as well as a staff field(select option). When HR uploads a document for a specific staff member, it will only be visible to that particular staff member. | 5 | 4 | pending
3 | xeon | Human Resource | Add button is not working in Account Details - Staff Creation Module | 4 | 0 | completed
DATE : 02-11-2023
S.NO | PROJECT | MODULE | TASK DESCRIPTION | Est.Time | Wrk.Time | Status
1 | xeon | Human Resource | The KRA & KPA forms implementation - includes a master form with multiple document upload fields, as well as a staff field(select option). When HR uploads a document for a specific staff member, it will only be visible to that particular staff member. | 5 | 1 | completed
2 | xeon | Human Resource | Add button is not working in Account Details - Staff Creation Module | 4 | 4 | completed
DATE : 03-11-2023
S.NO | PROJECT | MODULE | TASK DESCRIPTION | Est.Time | Wrk.Time | Status
1 | xeon | dashboard | Display Today's status as on-duty, late, or permitted. | 4 | on hold | onhold | discussion not completed
2 | xeon | Human Resource | Create a Master for employee expenses. | 16 | onhold | onhold | discussion not completed
DATE : 04-11-2023
S.NO | PROJECT | MODULE | TASK DESCRIPTION | Est.Time | Wrk.Time | Status
1 | xeon | dashboard | Display Today's status as on-duty, late, or permitted. | 4 | on hold | onhold
2 | xeon | Human Resource | Create a Master for employee expenses. | 16 | onhold | onhold
3 | xeon | Human Resource | dasboard and overall module testing | 4 | 4 | completed
DATE : 06-11-2023
S.NO | PROJECT | MODULE | TASK DESCRIPTION | Est.Time | Wrk.Time | Status
1 | xeon | dashboard | Display Today's status as on-duty, late, or permitted. | 4 | on hold | onhold
2 | xeon | Human Resource | Create a Master for employee expenses. | 16 | onhold | onhold
3 | xeon | Human Resource | Testing and fixing all existing bugs in entire application | 6 | 6.15 | completed